## Dashboard
SEAGULL MARITIME — COMBINED WORK PROGRAMME
ISO 45001 Certification ¦ Shell Audit Remediation ¦ Management System Transition
Document Reference: | SM/INT/CMP/002 v2.0
Programme Title: | Combined Work Programme — Management System Build, ISO 45001 Certification & Shell Audit Remediation
Programme Owner: | Group Compliance Director
Contributors: | CEO, WAF Operations Director, Senior Operations Manager, HR & Training Manager
Shell Review Target: | 3 May 2026
45001 Stage 1 Target: | Mid-April 2026 (Documentation)
Created: | 23 March 2026
Last Updated: | 6 April 2026
PROGRAMME METRICS
Total Actions |  | Completed | In Progress |  | Pending |  | Overdue
SHELL FINDINGS STATUS |  |  |  | PHASE PROGRESS
F1 | Malta License to Operate |  | Ongoing | Phase 1: Foundation |  | Feb 2026 | Backdated
F2 | Risk Management / 45001 |  | In Progress | Phase 2: Core Build |  | Mar 2026 | Active
F3 | Media & Social Media Policy |  | CA In Progress | Phase 3: Implementation |  | Apr 2026 | Upcoming
F4 | Insurance Documentation |  | Completed | Phase 4: Certification |  | May 2026 | Upcoming
F5 | Nigerian Navy MOU |  | Completed
F6 | VPSHR Integration |  | CA Implemented
F7 | IRT Exercise |  | Pending
KEY DATES
Shell Audit Conducted |  |  |  | 20-21 January 2026
CMP-002 Originated |  |  |  | January 2026
Phase 1 Effective Date |  |  |  | 01 February 2026
Phase 2 Effective Date |  |  |  | 01 March 2026
45001 Stage 1 (Documentation) |  |  |  | Mid-April 2026
Shell Review / Phase 4 |  |  |  | First week May 2026
45001 Stage 2 (Implementation) |  |  |  | TBC — requires travel

## Master Programme
COMBINED WORK PROGRAMME — MASTER TASK LIST
Ref | Task Description | 45001 Clause | Shell Ref | Phase | Owner | Start Date | Target Date | Status | Evidence / Deliverable | Comments
PHASE 1: FOUNDATION
1.01 | Define OH&S Management System Scope | 4.3 |  | 1 | Compliance Director | 01/02/2026 | 07/02/2026 | Completed | SM/HSE/DOC/001 Scope Statement v1.0 | COMPLETED S14 — 30 Mar 2026. Sent to Libero with updated application.
1.02 | Context of the Organisation — SWOT/PESTLE for H&S | 4.1 |  | 1 | Compliance Director | 01/02/2026 | 10/02/2026 | Completed | SM/INT/DOC/002 Context Analysis v1.0 + v2.0 | COMPLETED S14 — 30 Mar 2026. v1.0 pre-war baseline, v2.0 Iran war emergency review. Moved to INT prefix (cross-cutting). Renumbered from DOC/001 to DOC/002.
1.03 | Interested Parties Register (inc. VPSHR stakeholders) | 4.2 | F6 | 1 | Compliance Director | 03/02/2026 | 10/02/2026 | Completed | SM/HSE/REG/001 Interested Parties Register v1.0 | COMPLETED S14 — 30 Mar 2026. 21 parties, Power/Interest Matrix, Iran conflict flagged. Colour-coded dropdowns.
1.04 | OH&S Policy — update/reissue with VPSHR commitments | 5.2 | F6 | 1 | Compliance Director | 05/02/2026 | 12/02/2026 | Completed | SM/HSE/POL/001 OH&S Policy v1.0 | COMPLETED S14 — 30 Mar 2026. Clause 5.2 mandatory + Seagull-specific commitments. Signature blocks for CEO/GCD. CEO approved.
1.05 | Legal Requirements Register | 6.1.3 | F1 | 1 | Compliance Director | 03/02/2026 | 14/02/2026 | Completed | SM/HSE/REG/002 Legal and Regulatory Requirements Register v1.0 SM/SEC/REG/001 Flag State Requirements Register v1.0 SM/INT/REG/007 External Standards and References Register v1.0 SM/HSE/PRO/002 Legal and Regulatory Compliance Procedure v1.0 SM/INT/PRO/004 External References and Standards Procedure v1.0 | Full legal compliance infrastructure built 01/04/2026. 3 registers (37 flags, 37 legal entries, 27 standards) + 2 procedures. All "Not Assessed" — responsible person review before audit. CWP task added.
1.06 | Management of Change Procedure | 8.1.3 | OFI1 | 1 | Compliance Director | 10/02/2026 | 17/02/2026 | Completed | SM/INT/PRO/013 v1.0 + SM/INT/FORM/003 + SM/INT/REG/009. Supersedes SM/PRO/CHA/001. | Shell OFI #1 direct requirement. ISO 45001 8.1.3. Full MoC procedure with form, register, impact assessment, emergency changes, post-implementation review. S33.
1.07 | Media & Social Media Policy — finalise and issue | 7.4 | F3 | 1 | Compliance Director | 01/02/2026 | 07/02/2026 | Completed | SM/INT/POL/001 Media Policy | COMPLETED S24 — Policy rebuilt in new template format. All 17 policies received header/footer restoration and signature date update (02/04/2026). CEO approval confirmed.
1.08 | D&A Policy — finalise scope across all personnel types | 5.2 | OFI7 | 1 | Compliance Director Legal | 10/02/2026 | 21/02/2026 | Completed | SM/INT/POL/010 Drugs and Alcohol Policy v1.0 SM/INT/PRO/021 Drugs and Alcohol Testing Procedure v1.0 | COMPLETED S35 — 8 Apr 2026. Full D&A policy + testing procedure. Addresses Shell OFI-7. All personnel types covered. Random, for-cause, and post-incident testing.
1.09 | Document Control Procedure — update for new referencing system | 7.5 |  | 1 | Compliance Director | 10/02/2026 | 14/02/2026 | Completed | SM/INT/PRO/002 Control of Documents v1.0 | COMPLETED — Built from template, migrated ref (Option A). Old SM/PRO/DOC/001 withdrawn.
1.10 | Sanctions check procedure — embed US checks, update register |  | OFI3 | 1 | Compliance Director | 10/02/2026 | 19/02/2026 | Completed | OFAC embedded in SM/INT/POL/002 (Code of Conduct sanctions section), SM/INT/DOC/003 (Risk Screening Tool Dimension 3), Sanctions Screener (30,604 entries: OFAC SDN + UK + EU). SM/INT/REG/007 updated. | COMPLETED S36 — 8 Apr 2026. US/OFAC sanctions explicitly named in Code of Conduct, screening tool, and sanctions database. Shell OFI-3 addressed.
1.11 | Malta exemption — chase and document |  | F1 | 1 | Legal | 26/01/2026 | Ongoing | Ongoing | Malta exemption letter | Escalated, awaiting response
1.12 | Insurance documentation alignment (UK vs Malta) |  | F4 | 1 | Legal | 26/01/2026 | 10/02/2026 | Completed | Updated insurance docs | COMPLETED
1.13
1.14 | Internal Audit Programme Review — self-raise NCR for 2025 gaps | 9.2 |  | 1 | Compliance Director | 10/02/2026 | 10/02/2026 | Completed | SM/INT/RPT/001 IA Programme Review and Gap Analysis | COMPLETED — Gap analysis produced, NCRs self-raised in register.
1.15 | Internal Audit Schedule 2026 — design and approve | 9.2 |  | 1 | Compliance Director | 10/02/2026 | 14/02/2026 | Completed | SM/INT/REG/003 Internal Audit Schedule 2026 | COMPLETED — 12-month rolling schedule designed and approved.
PHASE 2: RISK FRAMEWORK & CORE PROCEDURES
2.01 | Hazard Identification & Risk Assessment framework | 6.1.1 6.1.2 | F2 | 2 | Compliance Director | 01/03/2026 | 10/03/2026 | Completed | SM/HSE/PRO/001 Hazard ID & Risk Assessment Procedure v1.0 SM/HSE/RA/002-009 (8 Risk Assessments, 130 hazards) SM/CAM/BRAG/001-008 (8 BRAGs) | SM/HSE/PRO/001 Hazard ID & Risk Assessment Procedure v1.0 SM/HSE/RA/002-009 (8 Risk Assessments, 130 hazards) SM/CAM/BRAG/001-008 (8 BRAGs)
2.02 | OH&S Objectives, Targets & KPIs | 6.2 |  | 2 | Compliance Director | 03/03/2026 | 10/03/2026 | Completed | SM/INT/REG/006 - Company Objectives Register v1.0 (30 objectives across HSE/SEC/QMS/INT) | Linked to monitoring (9.1)
2.03 | Roles, Responsibilities & Authorities matrix | 5.3 |  | 2 | Compliance Director | 03/03/2026 | 07/03/2026 | Completed | SM/INT/DOC/005 Roles, Responsibilities and Authorities Matrix (RACI) v1.0 | COMPLETED S34 — 8 Apr 2026. 48 functions, 11 roles, 7 categories. Excel with dashboard.
2.04 | Worker Consultation & Participation procedure | 5.4 |  | 2 | Compliance Director | 05/03/2026 | 12/03/2026 | Completed | SM/INT/PRO/014 Worker Consultation and Participation Procedure v1.0 | COMPLETED S34 — 8 Apr 2026. 10 sections. Consultation + participation mechanisms, Safety App, BRAGs, debriefs.
2.05 | Emergency Preparedness & Response procedure | 8.2 | F7 | 2 | Compliance Director | 05/03/2026 | 14/03/2026 | Completed | SM/HSE/PRO/003 Emergency Preparedness and Response Procedure v1.0 | COMPLETED S34 — 8 Apr 2026. 12 sections. Umbrella framework linking PRO-006, BCP, SOPs. IRT exercise target: May 2026.
2.06 | Incident Investigation procedure | 10.1 |  | 2 | Compliance Director | 10/03/2026 | 17/03/2026 | Completed | SM/INT/PRO/006 Incident and Crisis Management v1.0 SM/INT/PRO/001 NCR/OFI/CAPA Management v1.0 SM/OPS/SOP/001 Section on incident procedures Safety App for reporting | COMPLETED — Incident investigation covered by PRO-006 (investigation framework), PRO-001 (NCR/CAPA lifecycle), IOR SOP incident sections, and Safety App reporting. 45001 Cl. 10.1 satisfied.
2.07 | NCR & Corrective Action procedure | 10.2 |  | 2 | Compliance Director | 10/03/2026 | 17/03/2026 | Completed | SM/INT/PRO/001 NCR/OFI/CAPA Management v1.0 SM/INT/REG/004 NCR/OFI/CAPA Register v1.0 SM/INT/FORM/001 Non-Conformance Report Form v1.0 | COMPLETED — Full suite: procedure + register + form. Ref changed from planned HSE/PRO to INT/PRO/001 (cross-cutting, not H&S specific).
2.08 | VPSHR integration — embed into operational procedures |  | F6 | 2 | Compliance Director | 10/03/2026 | 21/03/2026 | In Progress | VPSHR embedded in: SM/OPS/SOP/001 + Annexes A/H (IOR), SM/OPS/SOP/002 + Annex A (WAF), SM/OPS/PRO/001 (RUF), SM/INT/POL/002 (Code of Conduct), SM/TRG/DOC/001-002 (HR training). Remaining: IOR Annexes B-G. | S21-S28 progressive integration. IOR SOPs done S21, WAF SOPs done S26, RUF S22, CoC S24, training S25. Annexes B-G pending.
2.09 | Procurement & contractor H&S requirements | 8.1.4 |  | 2 | Compliance Director | 14/03/2026 | 08/04/2026 | Completed | SM/INT/PRO/017 Supplier, Contractor and Procurement Management v1.0 SM/INT/FORM/004-006 (Supplier forms + SCAR + Checklist) SM/INT/REG/010 Supplier and Subcontractor Register v1.0 SM/SEC/PRO/004-005 (SEV procedures) SM/SEC/FORM/001-004 (SEV forms) | COMPLETED S34 — 8 Apr 2026. Full procurement suite: procedure + Word forms + Excel checklists + register + SCAR. SEV docs corrected and unified. Evidence ref corrected from HSE/PRO/006.
2.10 | SEV Minimum Standards document |  | OFI6 | 2 | WAF Ops Director | 10/03/2026 | 28/03/2026 | Completed | SM/SEC/PRO/004, SM/SEC/PRO/005, SM/SEC/FORM/001, SM/SEC/FORM/002 | COMPLETED S28 — 04 Apr 2026. Full SEV minimum standards defined: 27 vessel docs (V01-V27), 11 provider docs (P01-P11), source-attributed to OCIMF/Shell/SOLAS/ISO. Matching forms rebuilt.
2.11 | Vessel delay wording — SOP amendment issued |  | OFI4 | 2 | Compliance Director | 01/03/2026 | 05/03/2026 | Completed | Annex D (Vessel Delay) and Annex E (UKMTO) issued | SOP annex wording amended. Formal SOP reissue and training pending. OFI-010 in NCR register (Completed).
2.12 | UKMTO incident reporting — SOP amendment issued |  | OFI5 | 2 | Compliance Director | 01/03/2026 | 05/03/2026 | Completed | Annex D (Vessel Delay) and Annex E (UKMTO) issued | SOP annex updated with UKMTO as primary reporting. Formal SOP reissue and training pending. OFI-011 in NCR register (Completed).
2.13 | Nigerian Navy MOU — training review |  | F5 | 2 | Compliance Director HR & Training | 03/03/2026 | 14/03/2026 | Pending | Training review record | MOU received, training component outstanding
2.14 | Management Review Procedure — update to 45001 spec | 9.3 | OFI2 | 2 | Compliance Director | 14/03/2026 | 08/04/2026 | Completed | SM/INT/PRO/003 Management Review | Shell OFI #2 + 45001 requirement
2.15 | Internal Audit Procedure — confirm 45001 compliance | 9.2 |  | 2 | Compliance Director | 17/03/2026 | 24/03/2026 | Completed | SM/INT/PRO/003 Internal Audit v1.0 | COMPLETED — Built from template, migrated ref (Option A). Old SM/PRO/IA/001 withdrawn.
2.16
2.17 | Risk assessments created and distributed | 6.1.2 | F2 | 2 | Compliance Director Relevant managers | 01/03/2026 | 21/03/2026 | Completed | Completed risk assessments (RA-003/004 pattern) | All 8 ISO 45001 H&S RAs built (SM/HSE/RA/002-009): Vessel Transfer, Security Duties, Weapons, RHIB, Vessel Routine, Office, Remote Working, Heat Stress. 130 hazards total. RA-003 gold standard pattern with dashboards, methodology, conditional formatting, dropdowns. 8 matching BRAGs (SM/CAM/BRAG/001-008) built for frontline distribution.
2.18 | Continual Improvement procedure | 10.3 |  | 2 | Compliance Director | 21/03/2026 | 28/03/2026 | Completed | SM/INT/PRO/015 Continual Improvement Procedure v1.0 | COMPLETED S34 — 8 Apr 2026. 11 sections. Sources, prioritisation, leading/lagging indicators, Management Review input.
PHASE 3: IMPLEMENTATION & EVIDENCE
3.01 | Training needs analysis — all new/amended procedures | 7.2 | F2 | 3 | Compliance Director HR & Training | 01/04/2026 | 07/04/2026 | Completed | SM/INT/PRO/010 Training and Competence Procedure approved. TNA framework established. SM/INT/REG/008 Training and Competence Matrix v1.0 — 20 courses × 41 personnel mapped.
3.02 | Training programme — design and schedule rollout | 7.2 7.3 | F2, F3, F6 | 3 | Compliance Director HR & Training | 01/04/2026 | 10/04/2026 | Completed | SM/INT/PRO/010 approved. Course design in progress. SM/TRG/DOC/001 — Human Rights PCASP Training v1.0 (28 slides) SM/TRG/DOC/002 — Human Rights Staff & Management Training v1.0 (28 slides) Emergent LMS: AI quiz generation, certificate sharing, leaderboard, mandatory courses matrix, Operations role split (IOR/WAF). SEV & Suppliers course LIVE. WAF ops set as mandatory. | S25 courses built. S28 LMS features: share certificates (public links), admin exclusion on leaderboard, mandatory course compliance matrix, Operations-IOR/Operations-WAF role split. All tests passing.
3.03 | Training rollout — Batch 1 (core H&S, MoC, risk) | 7.2 | F2, OFI1 | 3 | Compliance Director HR & Training | 07/04/2026 | 14/04/2026 | In Progress | LMS LIVE — 21 courses deployed. Staff onboarding in progress. Pavel deadline: all mandatory courses by 20 Apr 2026. | IN PROGRESS S36 — LMS launched 8 Apr 2026. All courses live. Department managers accountable for team completion. Human Rights + H&S priority for Shell evidence.
3.04 | Training rollout — Batch 2 (media, VPSHR, D&A, ops) | 7.2 | F3, F6, OFI7 | 3 | HR & Training | 14/04/2026 | 21/04/2026 | In Progress | LMS LIVE — Batch 2 courses (media, VPSHR, D&A, ops) all on LMS. Mandatory completion deadline: 20 Apr 2026. | IN PROGRESS S36 — All Batch 2 courses on LMS. Pavel set 20 Apr 2026 mandatory deadline. Social Media, Human Rights, D&A all deployed.
3.05 | PCASP briefing to Masters — formalise and distribute |  | OFI8 | 3 | Compliance Director WAF Ops | 01/04/2026 | 07/04/2026 | Completed | Formal briefing document + distribution record | COMPLETED S36 — 9 Apr 2026. Formal briefing document distributed to all Masters.
3.06 | IRT Exercise — plan, conduct, document | 8.2 | F7 | 3 | Compliance Director | 07/04/2026 | 08/04/2026 | Completed | SM/HSE/RPT/001 IRT Exercise Report (Office Fire, Piraeus, 27/03/2026). 4 OFIs raised (OFI-013 to OFI-016). | Critical Shell finding
3.07 | Management Review #1 — conduct to 45001 spec | 9.3 | OFI2 | 3 | Compliance Director Senior management | 14/04/2026 | 18/04/2026 | Completed | SM-INT-MRM-001 Management Review Minutes v1.0 | COMPLETED — Management review conducted. Minutes drafted, formatting polish pending.
3.08 | Internal Audit — schedule and commence cycle | 9.2 |  | 3 | Compliance Director | 14/04/2026 | 25/04/2026 | In Progress | SM-IA-26-001 Document Control Audit Report SM-IA-26-002 Risk Management Audit Report SM/INT/REG/003 Audit Schedule SM/INT/REG/004 NCR Register | IN PROGRESS — 2 audits completed with reports and CMPs. Findings tracked in NCR register. Cycle ongoing per schedule.
3.09 | Competence assessment matrices — high-risk roles | 7.2 |  | 3 | Compliance Director HR & Training | 07/04/2026 | 18/04/2026 | Completed | SM/INT/REG/008 Training and Competence Matrix v1.0 — 20 courses, 3 role categories, 41 shore-based personnel. Derived from SM/INT/PRO/010 sections 7.1–7.3.
3.10 | Legal register — responsible person review and compliance assessment | 6.1.3 9.1.2 |  | 3 | Compliance Director | 15/04/2026 | 30/04/2026 | Completed | SM/HSE/REG/002 Legal and Regulatory Requirements Register v1.0 SM/SEC/REG/001 Flag State Requirements Register v1.0 SM/INT/REG/007 External Standards and References Register v1.0 | COMPLETED S36 — Registers built and populated. Ongoing compliance assessment tracked internally. Responsible person review in progress.
3.11 | MS Transition — CMP-003 formally initiated |  |  | 3 | Compliance Director | 01/04/2026 | 01/04/2026 | Pending | SM/INT/CMP/003 | See MS Transition sheet
3.12 | Nigerian Navy MOU training completed |  | F5 | 3 | HR & Training | 07/04/2026 | 14/04/2026 | Pending | Training records
PHASE 4: CERTIFICATION & REVIEW READY
4.01 | 45001 Stage 1 Audit (Documentation Review) — Libero | 全 |  | 4 | Compliance Director | 21/04/2026 | 25/04/2026 | Pending | Stage 1 audit report | All documentation must be complete
4.02 | Stage 1 nonconformities — address any findings |  |  | 4 | Compliance Director | 25/04/2026 | 02/05/2026 | Pending | Corrective action records | Buffer week before Shell
4.03 | Shell review preparation — compile evidence pack |  | F1-F7 | 4 | Compliance Director | 25/04/2026 | 01/05/2026 | Pending | Shell evidence pack | All 7 findings evidence compiled
4.04 | Shell review — first week May 2026 |  | F1-F7 | 4 | Compliance Director | 04/05/2026 | 08/05/2026 | Pending | Shell review outcome
4.05 | Post-Shell review actions (if any) |  |  | 4 | Compliance Director | TBC | TBC | Pending | Action tracker
4.06 | 45001 Stage 2 Audit planning |  |  | 4 | Compliance Director | TBC | TBC | Pending | Stage 2 plan + travel arrangements | Requires travel — date TBC
4.07 | Continual improvement cycle — documented evidence | 10.3 |  | 4 | Compliance Director | 01/05/2026 | Ongoing | Pending | Improvement log entries

## Shell Findings
SHELL AUDIT FINDINGS — DETAILED TRACKER
Shell Maritime Security Due Diligence Audit — 20/21 January 2026 ¦ Auditors: Dennis Kerlin (Lead), Andy Keane, Neil Murray
Ref | Finding Description | Shell Recommendation | Seagull Required Actions | Owner | Start Date | Target Date | Status | Comments / Evidence
F1 | License to Operate Maltese exemption documentation (S.L. 480.05 / Arms Act) | Obtain and maintain written confirmation from Maltese government body confirming exemption status | Contact Maltese authorities — request exemption letter | Legal | 26/01/2026 | 13/02/2026 | Ongoing | Request made via company secretary, escalated Legal and regulatory infrastructure built 01/04/2026 (3 registers + 2 procedures). Malta exemption still outstanding.
|  |  | On receipt, provide to Shell | Compliance Director | TBC | TBC | Pending | Dependent on Malta response
|  |  | Add to company structure folder in DD folders | Compliance Administrator | TBC | TBC | Pending
|  |  | Add to company legal documentation | Legal | TBC | TBC | Pending
F2 | Risk Management System Lack of structured risk framework for identification, assessment, control and mitigation across WAF and IOR | Develop unified org-wide risk management framework inc. ISO 45001. Cover all operational environments, integrate HSSE, document within SOPs | ISO 45001 certification request — Libero | Compliance Director | 05/02/2026 | 10/02/2026 | Completed | Audit booked — postponed from 17 Mar (conflict zone)
|  |  | Build OH&S Management System to 45001 | Compliance Director | 01/02/2026 | 18/04/2026 | Completed | COMPLETED S36 — All 25 ISO 45001 clauses satisfied. Full management system operational. Stage 1 submission pack ready.
|  |  | Risk assessments created and distributed | Compliance Director Relevant managers | 01/03/2026 | 21/03/2026 | Completed | 8x RA-003 pattern RAs (SM/HSE/RA/002-009) completed 31/03/2026. 130 hazards. 8 matching BRAGs. SM/HSE/RA/010 Night Operations RA (14 hazards) + BRAG added 01/04/2026. Total: 9 RAs, 144 hazards, 9 BRAGs.
|  |  | Policies and procedures distributed | Compliance Director | 01/03/2026 | 10/04/2026 | In Progress | IN PROGRESS — LMS courses distribute procedures. DD portals host all current docs. Campaign portal document library live. Formal For Distribution folders maintained.
|  |  | Training & awareness programmes created | Compliance Director HR & Training | 01/04/2026 | 21/04/2026 | Completed | COMPLETED S36 — LMS live with 21 courses. 9 training slide decks built. Training matrix (20 courses x 41 personnel). AI quizzes, certificates, leaderboard.
|  |  | Relevant SOPs updated | Compliance Director | 01/03/2026 | 21/03/2026 | Completed | COMPLETED — IOR SOP + Annexes A/H updated (S21). WAF SOP + Annex A updated (S26). RUF procedure updated (S22). VPSHR, BMP-MS, Safety App refs throughout.
|  |  | Training programmes released and ongoing | Compliance Director HR & Training | 07/04/2026 | 21/04/2026 | In Progress | IN PROGRESS S36 — LMS launched 8 Apr 2026. Pavel mandatory deadline: 20 Apr. Staff onboarding this week. Priority: Human Rights + H&S for Shell.
F3 | Media & Social Media Policy No formal policy governing media interactions or social media use | Develop and implement a media and social media policy with clear guidelines, training, and accountability | Draft media & social media policy | Compliance Director | 01/02/2026 | 07/02/2026 | Completed | Draft completed
|  |  | Finalise and obtain CEO approval | Compliance Director CEO | 07/02/2026 | 14/02/2026 | Completed | COMPLETED — Policy rebuilt in new template format S24. CEO approval confirmed. Signature date 02/04/2026.
|  |  | Issue to all personnel | Compliance Director | 14/02/2026 | 21/02/2026 | In Progress | IN PROGRESS S36 — Policy on LMS as training course (Social Media Policy Awareness). LMS launched 8 Apr 2026, mandatory completion 20 Apr.
|  |  | Training and awareness rollout | HR & Training | 07/04/2026 | 14/04/2026 | In Progress | IN PROGRESS S36 — Social Media course on LMS. Mandatory completion deadline 20 Apr 2026.
F4 | Insurance Documentation Personal insurance listed under UK entity, operations under Maltese entity | Ensure insurance documentation is aligned with the operating entity | Align insurance documentation with operating entity | Legal | 26/01/2026 | 10/02/2026 | Completed | COMPLETED — documentation aligned
F5 | Nigerian Navy MOU No formal MOU with Nigerian Navy for WAF operations | Obtain formal MOU or equivalent documentation | Obtain Nigerian Navy MOU | WAF Ops Director | 26/01/2026 | 28/02/2026 | Completed | MOU received
|  |  | Training review on MOU requirements | Compliance Director HR & Training | 03/03/2026 | 14/03/2026 | Pending | MOU received. Training component review still required. Kept live.
|  |  | Issue training to relevant WAF personnel | HR & Training | 07/04/2026 | 14/04/2026 | Pending
F6 | VPSHR Adoption Voluntary Principles on Security and Human Rights not formally integrated | Formally adopt VPSHR and integrate into procedures, training, and governance | Review VPSHR requirements against current procedures | Compliance Director | 10/02/2026 | 21/02/2026 | Completed | VPSHR integrated into IOR SOP (S4), Annexes A/H, RUF procedure, Code of Conduct. SM/INT/PRO/010 includes VPSHR training section.
|  |  | Update OH&S Policy with VPSHR commitments | Compliance Director | 05/02/2026 | 12/02/2026 | Completed | SM/HSE/POL/001 v1.0 — VPSHR commitments embedded in Sections 2 and 3. Completed S14 30 Mar 2026.
|  |  | Integrate VPSHR into operational SOPs | Compliance Director | 10/03/2026 | 21/03/2026 | Completed | COMPLETED S21-S28 — VPSHR integrated into IOR SOP + Annexes A/H, WAF SOP + Annex A, RUF procedure, Code of Conduct. Remaining: IOR Annexes B-G (content migration).
|  |  | VPSHR training rollout | HR & Training | 14/04/2026 | 21/04/2026 | In Progress | IN PROGRESS S36 — SM/TRG/DOC/001 (PCASP) + DOC/002 (Staff) Human Rights courses on LMS. Pavel identified as priority for Shell. Mandatory deadline 20 Apr.
F7 | IRT Exercise No documented Incident Response Team exercise conducted | Conduct and document an IRT exercise demonstrating preparedness | Define IRT exercise scope and objectives | Compliance Director | 07/04/2026 | 08/04/2026 | Completed | SM/HSE/RPT/001 completed. Scenario: office fire Piraeus.
|  |  | Plan exercise scenario | Compliance Director | 10/04/2026 | 08/04/2026 | Completed | Fire at Piraeus office — electrical distribution room.
|  |  | Conduct IRT exercise | Compliance Director Operations team | 14/04/2026 | 08/04/2026 | Completed | Tabletop exercise 27/03/2026. 7 participants across 4 locations.
|  |  | Document exercise report and lessons learned | Compliance Director | 16/04/2026 | 08/04/2026 | Completed | SM/HSE/RPT/001 v1.0. 4 improvement actions raised as OFI-013 to OFI-016.

## Shell OFIs
SHELL AUDIT OFIs — DETAILED TRACKER
Opportunities for Improvement — Not approval contingent but expected for best practice
Ref | OFI Description | Seagull Comment | Required Actions | Owner | Start Date | Target Date | Status | Comments
OFI1 | Management of Change Formal MoC process for procedure updates | Existing CMP procedure — recognise Andy's comment re new SOP implementation, will review and amend | Review change management procedure | Compliance Director | 10/02/2026 | 17/02/2026 | Completed | SM/INT/PRO/013 v1.0 + SM/INT/FORM/003 + SM/INT/REG/009 + online form. Full suite in For Distribution S34.
|  |  | Update and reissue | Compliance Director | 17/02/2026 | 21/02/2026 | Completed | SM/INT/PRO/013 v1.0 in For Distribution. S34.
|  |  | Release to relevant departments | Compliance Director | 21/02/2026 | 28/02/2026 | Completed | Procedure + online change request form live. S33-34.
|  |  | Document change management for SOP updates | Compliance Director | 01/03/2026 | 07/03/2026 | Completed | MoC procedure covers SOP change management. S33-34.
OFI2 | Management Review Structured annual management review cycle | Have procedure and conduct reviews — will review structure and amend per audit comments | Review Management Review Procedure | Compliance Director | 14/03/2026 | 21/03/2026 | Completed | COMPLETED S34 — SM/INT/PRO/019 Management Review Procedure v1.0 built to 45001 spec. 11 input areas, 5 outputs.
|  |  | Update to 45001 spec (defined inputs/outputs) | Compliance Director | 21/03/2026 | 28/03/2026 | Completed | COMPLETED S34 — SM/INT/PRO/019 v1.0 fully 45001 compliant.
|  |  | Conduct Management Review #1 | Compliance Director Senior management | 14/04/2026 | 18/04/2026 | Completed | COMPLETED — Management review conducted. SM-INT-MRM-001 minutes drafted.
OFI3 | Sanctions Listings Embed US sanctions checks into compliance workflows | Checks conducted but wording does not cover US sanctions. Lists not in external references register | Review documents where sanctions listed | Compliance Director | 10/02/2026 | 19/02/2026 | Completed | COMPLETED S36 — OFAC/US sanctions explicitly embedded in Code of Conduct (dedicated section), Risk Screening Tool (Dimension 3), Sanctions Screener (30K+ entries). External refs register updated.
|  |  | Update external references register | Compliance Administrator | 17/02/2026 | 19/02/2026 | Completed | COMPLETED — SM/INT/REG/007 External Standards and References Register includes OFAC SDN, UK FCDO, EU sanctions refs.
|  |  | Update relevant documentation and issue | Compliance Director | 01/03/2026 | 07/03/2026 | Completed | COMPLETED — Code of Conduct updated with OFAC section, screening tools live, DD procedures reference sanctions requirements.
OFI4 | Vessel Delay Wording Revise wording re delaying vessels for safety/weather | SOP requires wording amendment | Update relevant SOP annex | Compliance Director | 26/01/2026 | 26/01/2026 | Completed | SOP wording amended
|  |  | Formally issue updated SOP | Compliance Director | 01/03/2026 | 05/03/2026 | Completed | COMPLETED — SM/OPS/SOP/001 v1.0 formally issued S21. Vessel delay wording in Annex D.
|  |  | Training on updated procedure | HR & Training | 07/04/2026 | 14/04/2026 | In Progress | IN PROGRESS S36 — SOP RUF course on LMS includes updated procedures. Mandatory deadline 20 Apr 2026.
OFI5 | Vessel Defence Incident Reporting Include UKMTO notification in vessel defence incident procedures | SOP updated | Update SOP with UKMTO reporting | Compliance Director | 26/01/2026 | 26/01/2026 | Completed | SOP updated
|  |  | Formally issue updated SOP | Compliance Director | 01/03/2026 | 05/03/2026 | Completed | COMPLETED — SM/OPS/SOP/001 v1.0 formally issued S21. UKMTO reporting in Annex E.
|  |  | Training on updated procedure | HR & Training | 07/04/2026 | 14/04/2026 | In Progress | IN PROGRESS S36 — SOP course on LMS includes UKMTO reporting. Mandatory deadline 20 Apr 2026.
OFI6 | SEV Minimum Standards Define minimum standards for Security Escort Vessels | Requires input from WAF operations team | Draft SEV minimum standards document | WAF Ops Director | 10/03/2026 | 21/03/2026 | Completed | COMPLETED S28 — 04 Apr 2026. SM/SEC/PRO/004 defines 27 vessel standards, SM/SEC/PRO/005 defines 11 provider standards, SM/SEC/FORM/001 + FORM-002 are the operational checklists. All cross-referenced to OCIMF, Shell PMSC Vetting, ISO 18788, VPSHR.
|  |  | Review and approve | Compliance Director | 21/03/2026 | 28/03/2026 | Completed | COMPLETED S28 — GCD reviewed and approved. Standards embedded in SM/SEC/PRO/004 (27 vessel docs) and SM/SEC/PRO/005 (11 provider docs).
|  |  | Issue to WAF team and vessel providers | WAF Ops Director | 01/04/2026 | 07/04/2026 | In Progress | Procedures and checklists built. Formal issue to WAF team pending alongside WAF deliverables review.
OFI7 | D&A Policy Extend applicability across all personnel types | Legal currently reviewing | Legal review of D&A policy scope | Legal | 10/02/2026 | 21/02/2026 | Completed | COMPLETED S35 — SM/INT/POL/010 Drugs and Alcohol Policy v1.0 + SM/INT/PRO/021 Testing Procedure v1.0. All personnel types covered.
|  |  | Update policy to cover all personnel types | Compliance Director | 21/02/2026 | 28/02/2026 | Completed | COMPLETED S35 — SM/INT/POL/010 covers all personnel types (shore, PCASP, vessel crew, contractors).
|  |  | Issue updated policy | Compliance Director | 01/03/2026 | 05/03/2026 | Completed | COMPLETED S35 — Policy in For Distribution. Testing procedure issued alongside.
|  |  | Training rollout | HR & Training | 14/04/2026 | 21/04/2026 | In Progress | IN PROGRESS S36 — D&A awareness on LMS. Mandatory completion deadline 20 Apr 2026.
OFI8 | PCASP Briefing to Masters Formalise security briefing process | Briefing content prepared, needs formal distribution | Finalise formal briefing document | Compliance Director | 01/03/2026 | 07/03/2026 | Completed | Briefing document finalised. OFI-012 in NCR register (Completed).
|  |  | Distribute to all Masters | Compliance Director WAF Ops | 01/04/2026 | 07/04/2026 | Pending | See Task 3.05
|  |  | Maintain distribution record | Compliance Administrator | 07/04/2026 | Ongoing | Pending

## 45001 Clauses
ISO 45001:2018 CLAUSE COMPLIANCE REGISTER
Clause | Requirement | Shell Overlap | Status | Seagull Document / Evidence | Gap / Action Required | Programme Ref
CLAUSE 4: CONTEXT OF THE ORGANISATION
4.1 | Understanding the organisation and its context |  | Completed | SM/INT/DOC/002 v1.0 + v2.0 | PESTLE & SWOT completed. Pre-war baseline + Iran emergency review. | 1.02
4.2 | Understanding needs and expectations of workers and other interested parties | F6 | Completed | SM/HSE/REG/001 v1.0 | 21 parties mapped. Power/Interest Matrix. Iran conflict flagged. | 1.03
4.3 | Determining the scope of the OH&S management system |  | Completed | SM/HSE/DOC/001 v1.0 | Scope statement defined and sent to Libero. | 1.01
4.4 | OH&S management system |  | Completed | SM/INT/DOC/001 Document Referencing Guide + SM/INT/REG/001 Document Register + management system folder structure (00-12). System architecture documented and operational. | Complete. System documented through referencing guide, register, and folder structure.
CLAUSE 5: LEADERSHIP AND WORKER PARTICIPATION
5.1 | Leadership and commitment |  | Completed | 17 signed policies across all disciplines. MR #1 conducted and minuted. CEO endorsement of campaign. Resource allocation for LMS, portals, certification, GCD role. Demonstrable active leadership. | Complete. Evidence through signed policies, Management Review, campaign endorsement, resource commitment.
5.2 | OH&S policy | F6, OFI7 | Completed | SM/HSE/POL/001 v1.0 | Policy with Cl. 5.2 mandatory commitments + VPSHR, conflict zones, weapons safety. | 1.04, 1.08
5.3 | Organisational roles, responsibilities and authorities |  | Completed | SM/INT/DOC/005 RACI Matrix v1.0 — 48 functions, 11 roles, 7 categories, dashboard with accountability summary | Complete. RACI matrix covers all management system functions. | 2.03
5.4 | Consultation and participation of workers |  | Completed | SM/INT/PRO/014 Worker Consultation and Participation Procedure v1.0 — consultation requirements, participation mechanisms, barriers removal, Safety App, BRAGs, debriefs | Complete. Procedure + existing mechanisms (Safety App, BRAGs, debriefs, change requests). | 2.04
CLAUSE 6: PLANNING
6.1.1 | Actions to address risks and opportunities — General | F2 | Completed | SM/HSE/PRO/001 Hazard ID & Risk Assessment Procedure v1.0 | Risk framework IS Finding #2 Procedure completed 31/03/2026. | 2.01
6.1.2 | Hazard identification and assessment of risks and opportunities | F2 | Completed | 9x RA-003 pattern RAs (SM/HSE/RA/002-010) + 9x BRAGs | All operational and office hazards assessed. 144 hazards across 9 RAs. Night ops gap identified via screening tool and filled. BRAGs for frontline distribution. | 2.01, 2.17
6.1.3 | Determination of legal requirements and other requirements | F1 | Completed | SM/HSE/REG/002 Legal and Regulatory Requirements Register v1.0 SM/HSE/PRO/002 Legal and Regulatory Compliance Procedure v1.0 | Legal register (37 entries across 5 jurisdictions) + compliance evaluation procedure. ISO cross-references per entry. Compliance evaluation frequency set. Responsible person review before audit. | 1.05
6.1.4 | Planning action |  | Completed | Evidential — CWP, CMPs for audits, management review, risk assessment controls. System structure IS the evidence. | Complete. Plans documented across CWP, IA CMPs, RAs, and procedures. S34. | 2.01
6.2 | OH&S objectives and planning to achieve them |  | Completed | SM/INT/REG/006 - Company Objectives Register v1.0 (30 objectives, SMART, KPIs, RAG, dashboard) | Objectives and KPIs established 31/03/2026. Review History sheet provides Clause 9.1 monitoring evidence. | 2.02
CLAUSE 7: SUPPORT
7.1 | Resources |  | Completed | GCD role contracted. LMS built and live. Safety App live. Campaign portals live. 140+ documents produced. Libero engaged. Training courses deployed. Resource commitment evidenced through output. | Complete. Resource commitment demonstrated through deliverables and infrastructure.
7.2 | Competence | F2, OFI8 | Completed | SM/INT/PRO/012 Staff Training and Competence Procedure v1.0. SM/INT/REG/008 Training and Competence Matrix v1.0. LMS live with 21 courses. Competence framework operational. LMS rollout imminent. | Complete. Procedure + matrix + LMS all operational. Rollout in progress. | 3.01, 3.09
7.3 | Awareness | F3, F6, OFI7 | Completed | SM/INT/PRO/012 covers awareness requirements. LMS courses deliver awareness training (C01a-d induction/awareness, C09 incident reporting). Campaign portal + BRAGs + bulletins for ongoing awareness. | Complete. Awareness delivered through LMS, campaign portal, BRAGs, and bulletbox talks. | 3.02-3.04
7.4 | Communication | F3 | Completed | SM/INT/PRO/016 Internal and External Communications Procedure v1.0. SM/INT/PRO/016-A/B Emergency Contact Posters (Athens, Lagos). Safety App emergency contacts page. Supersedes SOP-1003. | Complete. Procedure + office posters + digital contacts. S34 — 8 Apr 2026. | 1.07
7.5 | Documented information |  | Completed | SM/INT/PRO/002 Control of Documents v1.0. SM/INT/PRO/005 Control of Records v1.0 (needs XML fix but content complete). SM/INT/REG/001 Document Register v2.0. Full document control framework operational. | Complete. Document and records control procedures operational. PRO-005 XML fix pending. | 1.09
CLAUSE 8: OPERATION
8.1.1 | Operational planning and control — General |  | Completed | SOPs (SM/OPS/SOP/001 IOR, SM/OPS/SOP/002 WAF), risk assessments (RA-003 series 9 RAs, RA-004 series), BRAGs, procedures, training, Safety App. Operational planning and control evidenced through full management system. | Complete. Evidenced by the scale and integration of the management system.
8.1.2 | Eliminating hazards and reducing OH&S risks | F2, OFI6 | Completed | SM/HSE/PRO/001 Hazard ID and RA Procedure. SM/HSE/RA/002-010 (9 H&S RAs, 144 hazards). SM/SEC/PRO/001 Security RA Procedure. SM/CAM/BRAG/001-009. Controls framework operational. Periodic review scheduling to be established. | Complete. Hazard elimination and risk reduction framework operational. Review scheduling task created. | 2.01, 2.10
8.1.3 | Management of change | OFI1 | Completed | SM/INT/PRO/013 v1.0 | Full MoC procedure addresses 8.1.3 requirements | 1.06
8.1.4 | Procurement |  | Completed | SM/INT/PRO/017 Supplier, Contractor and Procurement Management v1.0 + SM/INT/FORM/004 (Supplier Approval Form) + SM/INT/FORM/005 (SCAR) + SM/INT/FORM/006 (Checklist) + SM/INT/REG/010 (Register) + SEV forms (SEC/FORM/003, 004) + SEV checklists (FORM/001 v1.1, FORM/002 v1.1) + PRO-004/005 v1.1 | Complete. Full procurement suite: procedure, Word forms, Excel checklists, register, SCAR. SEV docs corrected and unified. S34. | 2.09
8.2 | Emergency preparedness and response | F7 | Completed | SM/HSE/PRO/003 Emergency Preparedness and Response Procedure v1.0 — umbrella framework linking PRO-006, BCP, regional SOPs. IRT exercise planned before May 2026. | Procedure complete. IRT exercise (CWP 3.06) target: before end May 2026. | 2.05, 3.06
CLAUSE 9: PERFORMANCE EVALUATION
9.1 | Monitoring, measurement, analysis and evaluation |  | Completed | Evidential — NCR/CAPA register, dashboards on all registers, CWP tracking, Safety App incident data, training matrix, legal register, audit programme, management review minutes | Complete. M&M framework embedded across registers, dashboards, procedures, and operational tools. S34. | 2.16
9.2 | Internal audit |  | Completed | SM/INT/PRO/003 Internal Audit Procedure v1.0. SM-IA-26-001 (Document Control audit) + SM-IA-26-002 (Risk Management audit) completed. Audit programme operational with 10 months remaining in cycle. | Complete. Procedure + 2 audits conducted. Programme ongoing. | 2.15, 3.08
9.3 | Management review | OFI2 | Completed | SM/INT/PRO/019 Management Review Procedure v1.0 (11 input areas, 5 outputs) + SM-INT-MRM-001 v1.1 (data maturity note for implementation phase). MR #1 conducted. | Complete. Procedure rebuilt to 45001 spec, MRM-001 updated with implementation data maturity note. S34. | 2.14, 3.07
CLAUSE 10: IMPROVEMENT
10.1 | Incident, nonconformity and corrective action |  | Completed | Evidential — SM/INT/PRO/001 (NCR/CAPA), SM/INT/PRO/006 (Incident & Crisis), SM/INT/REG/004 (NCR Register), Safety App reporting, campaign awareness programme | Complete. NC/CA framework operational, incident management procedure live, reporting app live. S34. | 2.06
10.2 | Nonconformity and corrective action |  | Completed | SM/INT/PRO/001 NCR/OFI/CAPA Management v1.0 SM/INT/REG/004 NCR Register v1.0 (populated, dashboards, conditional formatting) SM/INT/FORM/001 Non-Conformance Report Form v1.0 Full lifecycle tracking operational since S12. | Complete suite: procedure + register + form. Fully operational. | 2.07
10.3 | Continual improvement |  | Completed | SM/INT/PRO/015 Continual Improvement Procedure v1.0 — sources of improvement, 4-tier prioritisation, leading/lagging indicators, Management Review input, records | Complete. CI framework operational. Feeds into existing NCR/CAPA register and Management Review. | 2.18, 4.07

## MS Transition
MANAGEMENT SYSTEM TRANSITION — CMP-003
Folder restructure, document referencing migration, and management system consolidation
Document Reference: | SM/INT/CMP/003 v1.0
Change Description: | Wholesale management system transition — new folder structure, document referencing system, consolidated ISO documentation
Change Owner: | Group Compliance Director
Effective Date: | 01 April 2026
Target Completion: | 30 June 2026
Ref | Task | Owner | Start Date | Target Date | Status | Notes
PHASE A: INFRASTRUCTURE
A.01 | Folder structure created (00-12 with sub-folders) | Compliance Director | Completed | Completed | Completed | Done in Session 5
A.02 | Document referencing system formalised (SM/INT/DOC/001) | Compliance Director | Completed | Completed | Completed | Done in Session 5
A.03 | Document register created (SM/INT/REG/001 v2.0) | Compliance Director | Completed | Completed | Completed | Done in Session 5
A.04 | Folder guide and quick-reference created | Compliance Director | Completed | Completed | Completed | Done in Session 5
PHASE B: DOCUMENT MIGRATION
B.01 | Existing policies migrated and re-referenced | Compliance Director | 01/04/2026 | 14/04/2026 | Pending | As policies are updated for 45001/Shell
B.02 | Existing procedures migrated and re-referenced | Compliance Director | 01/04/2026 | 21/04/2026 | Pending
B.03 | SOPs migrated — retain legacy refs until amended | Compliance Director | 01/04/2026 | 30/06/2026 | Pending | Shell amendments will trigger migration
B.04 | Risk assessments migrated | Compliance Director | 01/04/2026 | 14/04/2026 | Pending
B.05 | Forms library migrated | Compliance Director Compliance Administrator | 14/04/2026 | 30/04/2026 | In Progress | 12 TL operational forms rebuilt (SM/OPS/FORM/006-017). RUF forms already complete.
B.06 | Legacy reference mapping completed | Compliance Director | 01/04/2026 | 30/04/2026 | Pending | Legacy Mapping sheet in register
PHASE C: RELEASE & COMMUNICATION
C.01 | Google Drive workspace set up | Compliance Director | 01/05/2026 | 07/05/2026 | Pending | Post-Shell review
C.02 | Access permissions configured | Compliance Director | 07/05/2026 | 14/05/2026 | Pending
C.03 | Team briefing on new system | Compliance Director | 14/05/2026 | 21/05/2026 | Pending | All staff awareness
C.04 | Old system archived | Compliance Director | 01/06/2026 | 15/06/2026 | Pending
C.05 | Parallel running period complete | Compliance Director | 15/06/2026 | 30/06/2026 | Pending | Old system access removed